

Newforma Project Center Commitments Quick Reference Guide

Tenth Edition

Table of Contents

[Commitments: Contracts, Potential Change Orders, and Change Orders 1](#_Toc352679118)

[Initial Considerations 1](#_Toc352679119)

[Process Overview 2](#_Toc352679120)

[Create a Contract 2](#_Toc352679121)

[Merge the Contract Document 3](#_Toc352679122)

[Forward the Contract for Review or Signature 4](#_Toc352679123)

[Record the Reviewer Response for the Contract 4](#_Toc352679124)

[Link the Executed Contract File 5](#_Toc352679125)

[Close (Finalize) the Contract 5](#_Toc352679126)

[Create a Potential Change Order 5](#_Toc352679127)

[Generate a Letter to Request Pricing for the PCO 7](#_Toc352679128)

[Record Pricing for the PCO 8](#_Toc352679129)

[Track and Analyze PCOs and Commitments 9](#_Toc352679130)

[Turn PCO’s into Change Orders 9](#_Toc352679131)

[Merge the Change Order Document 11](#_Toc352679132)

[Forward the Change Order for Review or Signature 12](#_Toc352679133)

[Record the Reviewer Response for the Change Order 12](#_Toc352679134)

[Link the Change Order File 13](#_Toc352679135)

[Close (Finalize) a Change Order 14](#_Toc352679136)

[Close (Finalize) a Potential Change Order 14](#_Toc352679137)

Newforma® Tenth Edition Commitments Quick Reference Guide

Commitments: Contracts, Potential Change Orders, and Change Orders

**Purpose:** A “commitment” is a contractual obligation to pay another company, such as a supplier, subcontractor, or consultant. In Newforma Project Center you can track the complete commitment workflow in the Contracts, Potential Change Orders, and Change Orders activity centers.  
The Commitments feature group does not directly address management of the Owner contract in Tenth Edition.

**Audience:** Project team members involved in Contract Management and administration including Project Managers and Subcontractors.

**Key Features:**


* Create and track Contract scope including cost code-level of detail for Contract financial commitments.
* Create Contract, PCO, and Change Order documents ready for signature using Word templates that are customizable.
* Manage Potential Change Orders affecting Contracts, request and track pricing, and understand the big picture from the PCO Scoreboard.
* Create Change Orders from one or multiple PCO’s, and track the review and approval workflow.
* View summarized information of the Contract’s financial status, including all Change Orders and Potential Change Orders, and quickly drill-down into the related documents that compose the financial forecast.

Initial Considerations

Before you create a Contract record, you should consider doing the following:

1. **Create Cost Codes:** (Required) Cost Codes are required when entering a Schedule of Values for a Contract. In the Cost Codes activity center, add codes individually or use the Import Spreadsheet utility to create in bulk.
2. **Add Contract Documents in the Document Control activity center:** (Optional) Drawings, specifications, and contract exhibits provide the legal description of construction contracts. If you are using Newforma to generate contracts for signature, the current revisions of these documents should be tracked in the Document Control activity center so that they can be added into the Contract record. Optionally, the files can be transmitted along with the merged Contract document, PCO’s, and/or Change Orders.

Process Overview




Create a Contract

1. In the Contracts activity center, point to **New Contract** on the Tasks pane, and select **Create Contract**.



1. In the **Create Contract** dialog, fill in required fields such as **Subject**, **To Company**, and **From Company**. If you want to create a Contract document for signature through Newforma, select the correct Form Template. Complete any other detail fields.

***Note:*** *There are three default Word Form Templates provided. Each can be customized and/or you can create your own templates.*




1. Select the **Schedule of Values** tab to add commitment items to the Contract. Click the **Add New** button to add a new row, select **Cost Code** (required), enter the **Item** **Description** and **Commitment** amount. Add more line items for a detailed breakdown of the contract amount. The Total Commitment is displayed at the top of the grid.

***Note:*** *If you are creating a Contract record to just track a log of contract values, then this may be the only tab that is needed. The remaining steps in this section are primarily used if you are generating the contract documents for signature from Newforma.*



1. Select the **Scope** tab to describe the work that is included in the Contract. Click on the button to the far right of each section to enlarge the field. This information can be merged into the Contract document (except for Internal Notes).



1. Select the **Contract Docs** tab to add specific revisions of Record Documents from the Document Control activity center. These are the drawings, specifications, and contract exhibits that form the legal basis of the Contract. These files can be sent along with the merged Contract document.



1. Click **OK** when done to save the Contract record.


Merge the Contract Document

Once you have created the Contract record, you can optionally create the Contract document to be sent for signature using one of the default Word form templates, or using a form template you have customized or created.

1. Before you can create the Contract document, the correct Form Template must be selected in the Form Template field on the Contract record.



1. Select the Contract from the log view, and then click **View Form** from the Tasks pane.



1. The resulting merged Contract document will display. You can **Print**, or use the **Save As** button to save the file. If you are ready to take the next step, click the **Next Action** button and either **Forward** (for review or signature) or **Send** (if no response is required). This will create a PDF of the Contract and attach it to the Forward Contract workflow step.



Forward the Contract for Review or Signature

If you did not use the Next Action option in the previous step, you can use the separate **Forward** task to send for review or signature.

1. Select the Contract from the log view, and then click on **Forward** from the Tasks pane.




1. The Select Files to Forward for Review dialog will open. Select the Contract document(s) and/or other files to forward, select the method (Info Exchange or Email), then click OK.
2. The Forward Contract dialog box opens. Edit any information as needed, and then click the **Forward** button.
3. If Info Exchange was chosen as the forward method, fill out the Info Exchange options, and then click OK to complete the transfer.


Record the Reviewer Response for the Contract

When the reviewer response is received, it can be recorded as a workflow action for the Contract. Reviewer responses can originate from Info Exchange, Email, mail, etc., or from internal staff.

1. If internal staff is recording their review, select the Contract, click **Record Reviewer Response** from the Tasks pane, then go to step 3 below.



1. If the review response is coming from Info Exchange, it will be in the Pending Incoming log. Select the incoming response and click **Receive Pending Review Response** to receive it.



1. The Record Reviewer Response for Contract dialog box opens. Review the information, and then click **Record Response**.

Link the Executed Contract File

Once the Contract has been finalized and signed, you can link the signed, scanned file to the Contract record.


1. Select the Contract in the log and clicking on **Link the Executed Contract** **File** from the Tasks pane. Browse to find and select the file.



Close (Finalize) the Contract

After the Contract has been reviewed, and Contract documents have been signed and saved, you can take the next workflow action to Close (finalize) the Contract to indicate that the contracted work can begin.

1. Use the **Send and Close** option to send it to the parties involved.




1. The Select Files to Send dialog will open. Select the Contract document(s) and/or other files to send, select the method (Info Exchange or Email), then click OK.


Create a Potential Change Order

Use the Potential Change Order activity center to track issues that could possibly change the signed and finalized Contract.

1. To create a new PCO record, go to the Potential Change Orders activity center and click on **Create Potential Change Order** from the Tasks pane.




1. In the **Create Potential Change Order** dialog, fill in any required fields such as **Subject**, and then fill in any other details.




1. Click on the **Pricing** tab to add pricing data for the PCO. Click the **Add New** button to add a new row, and fill in an **Item Description**, **Contract**, **Cost Code**, and **Estimated Amount**. Repeat the process for each line you want to add. Use the **Create Similar** button to save data entry time for new rows added.


***Note:*** *If a Contract is selected, only Cost Codes assigned to that Contract are available. If no Contract has been selected for internal cost items, click the button in the Cost Code field to browse and select the appropriate Cost Code.*



1. Click on the **Description** tab to enter any general information about the PCO. Use the Internal Notes section to record any notes you do not want to be seen by external parties.



1. Click on the **Contract Docs** tab to add specific revisions of Record Documents from the Document Control activity center. These are the drawings, specifications, or contract exhibits that relate to the PCO. Background information that the subcontractors need in order to prepare their estimates can also be attached to the **Supporting Documents** tab.




1. Click **OK** when done to save the PCO.


Generate a Letter to Request Pricing for the PCO


Once you have created the PCO record with all applicable information, you can optionally create a letter to request pricing using one of the default Word form templates, or using a form template you have customized or created.


1. Select the PCO from the log view, and then click on **Generate Letter** from the Tasks pane.



1. The Generate Letter dialog will open. Select the **Pricing Items** you want to include. Then select the **Form Template** you want to use and the **Format**. Put in an **Output Filename** only if you want it to be called something other than the default name. Indicate a location in the **Save In** field for the letter only if you want it saved in a different place than the default location.   
     
   Click the **Preview** button to see the information merged before sending. If you are ready to send it, click the **Next Action** button and **Send**.




1. In the Send Options indicate how you want to send the document (Info Exchange or Email) and whether you want to create a Project Transmittal.
2. In the **Select Files to Send** dialog, you can optionally include the Contract Documents and/or Supporting Documents in the transfer along with the merged letter.
3. Then Modify the PCO, go to the Pricing tab, and indicate the date you requested pricing in the **Pricing Requested** field, the **Pricing Due Date**, and **Reminder Days**. 
4. You can also change the **Status** on the main PCO record to indicate that pricing has been requested.




Record Pricing for the PCO

Once you have created the PCO record with all applicable information, and requested pricing, as proposed pricing comes in you need to record it and track the status of all your PCO’s.

1. If the subcontractor responds via the Info Exchange website, the **Pricing Received** date, **Proposed Amount**, and **Proposed Days** will flow into the PCO line items automatically. If you receive pricing via email, verbally, or in person, you will need to fill in the information yourself.




1. Once all pricing has been received, you can change the **Status** of the PCO to **Pricing Completed**.




1. Once final amounts have been negotiated and agreed upon, fill in the **Approved Amounts** (and if needed, **Approved Days**) in order to create a Change Order.

***Note:*** *If any line on a PCO is not approved, enter zero in the Approved Amount field.*




Track and Analyze PCOs and Commitments

1. To see an instant on-screen analysis of a Potential Change Orders for tracking purposes, go to the Potential Change Order activity center and click on **Open Scoreboard** from the Tasks pane. The Scoreboard helps identify which pricing items need to be expedited. To print information from the Scoreboard, click on **Generate Report**.




1. To see an instant on-screen analysis of commitments for a Contract with a pie chart and summarized view of Change Orders and Potential Change Orders, go to the Contract activity center, select the Contract, and then click on the **Summary** tab.



Turn PCO’s into Change Orders

To finalize the agreement with a change order to the subcontractor, go to the Change Order activity center to create it.


1. In the Change Order activity center, point to **New Change Order** on the Tasks pane and click on **Create Change Order**.




1. In the **Create Change Order** dialog, fill in any required fields such as **Subject**, **Contract**, **To Company**, and **From Company**. Select the correct **Form Template**, and then fill in any other details.

***Note:*** *The Contract field is required if you are adding a Schedule of Values.*


***Note:*** *There are two default Form Templates provided. Each can be customized and/or you can create your own templates.*




1. Click on the **Schedule of Values** tab and click the **Add** button to add rows.




1. The dialog will allow you to select any Pricing Item that is tagged to the selected Contract and has an Approved Amount entered.



1. Click on the **Scope** tab to enter detailed information about what is included and not included in the Change Order, as well as other general information. Click on the button to the far right of each section to enlarge the field. Use buttons on the toolbar of each section for formatting text. This information will merge into the Change Order document (except for Internal Notes).



1. Optionally, you can click on the **Contract Docs** tab to transmit Record Documents related to the Change Order.



1. Fill information on other tabs as needed. Click **OK** when done to save the Change Order record.


Merge the Change Order Document

Once you have created the Change Order record with all applicable information, optionally you can create the Change Order document for signature using one of the default Word Form Templates, or using a form template you have customized or created.


1. Before you can create the Change Order document, the correct Form Template must be indicated in the Form Template field on the Change Order record.



1. Select the Change order from the log view, and then click **View Form** from the Tasks pane. Or, open the Change Order record, check the Next Action box and select View Form.




1. The merged Change Order document will appear. You can **Print**, or use the **Save As** button to save the PDF file. If you want to create the PDF and take the next step at the same time, click the **Next Action** button and either **Forward** (for review or signature), or **Send and Close**. Either of those actions will create a PDF of the Change Order document and attach it to the Forward Change Order workflow step.




Forward the Change Order for Review or Signature

Once the actual Change Order document has been created, saved in your project files, and linked to the Change Order record, if needed you can use the Forward workflow action if the document should be sent to someone for review or signature before finalizing.

1. Select the Change Order from the log view, and then click on **Forward** from the Tasks pane.




1. The Forward Change Order dialog box opens. Edit any information as needed, include any files on the **Files to Send** tab, and then click the **Forward** button.




Record the Reviewer Response for the Change Order

When the reviewer response is received, it can be recorded as a workflow action for the Change Order. Review responses can originate from Info Exchange, Email, mail, etc., or from internal staff.


1. If internal staff is recording their review, select the Change Order, click **Record Reviewer Response** from the Tasks pane, then go to step 3 below.



1. If the review response is coming from Info Exchange, it will be in the Pending Incoming log. Select the incoming response and click **Receive Pending Review Response** to receive it.



1. The Record Reviewer Response for Change Order dialog box opens. Review the information, and then click **Record Response**.




Link the Change Order File

Once the Change Order has been finalized and signed, you can link the signed, scanned file to the Change Order record.

1. Select the Change Order in the log and click on **Link Change Order File** from the Tasks pane. Browse to find and select the file. Or, instead of using this task, you can Modify the Change Order and click the button to the right of the **Executed Change Order** field to browse and find the file. It will then display on the Preview tab for quick reference.






Close (Finalize) a Change Order

After the Change Order has been reviewed, and documents have been signed, you can take the next workflow action to Close (finalize) the Change Order which may involve sending the finalized Change Order to the parties affected.

1. If you are sending the Change Order, select the Change Order from the log, then point to **Close** on the Tasks pane and click **Send and Close**.



1. If files are attached to the Change Order, the Select Files to Send dialog will open. Select the Change Order document(s) and/or other files to send, select the method (Info Exchange or Email), then click OK.

Close (Finalize) a Potential Change Order

After the PCO has been created, pricing has been requested and then recorded, and any needed Change Orders have been created, you can take the next workflow action to Close (finalize) the PCO to indicate that the issue has been resolved.

1. Modify the PCO and change the **Status** field to **Closed**, and then click OK.

